# CI Test Environment — Research & Level of Effort

# AWS Pre-prod Bamboo, Bitbucket & Artifactory

1. Purpose & Scope

This document captures the current state of the Conexus production CI/CD management environment Bamboo, Bitbucket, and Artifactory, and lays out the level of effort, dependencies, open questions, and cost/licensing considerations involved in standing up a dedicated CI test pre-prod environment, so that changes to Bamboo/Bitbucket/Artifactory configuration can be validated without risk to production CI.

Scope covers: an inventory of the existing production hosts and services,  the requirements already captured in, and a proposed work breakdown with estimated effort, cost, and risk callouts for team discussion.

2. Current Production CI/CD Environment

Production CI/CD runs across three EC2 instances in the management VPC. All three run Amazon Linux 2023, SELinux in permissive mode, and Docker (installed outside the package manager — not tracked by dnf/yum).

| Host | Instance Type | Role | Key Services (containers) |
| --- | --- | --- | --- |
| ip-10-56-112-34 (.34) | t3.2xlarge | Atlassian host | Bamboo server, Bitbucket, Postgres, NGINX (reverse proxy/TLS) |
| ip-10-56-112-35 (.35) | m6a.4xlarge | Bamboo build agents | Bamboo remote agents (Docker-based build execution) |
| ip-10-56-112-243 (.243) | m6i.xlarge | Artifactory host | Artifactory Pro, Postgres, NGINX (bundled JFrog image) |

## 2.1 .34 — Atlassian host (Bamboo + Bitbucket)

- OS / kernel: Amazon Linux 2023.11, kernel 6.1.158, up 105 days at time of capture.

- Storage: 150G root (/), separate 150G /app XFS volume (87% used — 130G/150G), 148G /mnt/temp ext4 scratch volume (48% used). Docker's data root is not on /app per fstab (line is commented out); container overlay2 data currently lives under /app/docker.

- Running containers (docker container ls):

  - prod-bamboo — atlassian/bamboo:10.2.11 — ports 8085, 8443

  - cnxs-mgmt-bitbucket — atlassian/bitbucket:9.4.17 — ports 7990, 7999

  - prod-postgres — postgres:16.5 — port 32768→5432 (host-mapped, non-default)

  - nginx — nginx:1.29.3 — ports 80, 443 (fronts both Bamboo and Bitbucket)

- Scheduled tasks (root crontab): nightly backup (02:15), weekly backup (Sun 03:00), daily Secrets Manager backup (01:55), staging cleanup (04:00) — all under /app/bamboobackup/atlassian-backups/bin/. CIS-mandated AIDE integrity check at 05:00. Legacy commented-out Bitbucket mirror cron jobs present but disabled.

- Shell access: root, ec2-user, plus team accounts (sikaj01, pgollt01, pkundm01, ezehb01).

## 2.2 .35 — Bamboo build agent host

- OS / kernel: Amazon Linux 2023.11, kernel 6.1.158, up 105 days.

- Storage: dedicated 500G ext4 volume mounted at /var/lib/docker (85% used — 396G/492G, the largest utilization of the three hosts) plus an LVM volume group (data_vg) split into /app (300G), /var (150G), /home (50G).

- Docker: dockerd actively running build containers (3.2G resident memory, ~4h CPU time at capture); images pulled from ECR include docker-jboss-local and conexus-postgres (339713019047.dkr.ecr.us-east-1.amazonaws.com/docker-local/…).

- No web-facing ports open besides SSH — this host only runs Bamboo remote agent containers that pull jobs from .34; no NGINX/Postgres services are exposed here despite being grouped with the "stack."

- Same team shell accounts as .34.

## 2.3 .243 — Artifactory host

- OS / kernel: Amazon Linux 2023.11, kernel 6.1.159, up 105 days.

- Storage: 800G XFS volume at /app/jfrog (52% used — 408G/800G) and a separate 200G XFS volume at /app/postgres (4% used — 7G/200G).

- Running containers (docker container ls):

  - artifactory-nginx — releases-docker.jfrog.io/jfrog/nginx-artifactory-pro:7.68.7 — ports 80, 443

  - artifactory — releases-docker.jfrog.io/jfrog/artifactory-pro:7.104.14 — port 8081 (internal only)

  - artifactory-postgres — postgres:15-alpine — port 5432 (internal only)

- Docker network: custom bridge "prod-net" connecting the three containers; no named Docker volumes — all persistent data is bind-mounted from /app/jfrog.

- Filestore backup directory (/app/jfrog/artifactory/var/data/artifactory/filestore-backup) uses Artifactory's sharded two-character hash directory structure and represents a large volume of objects to account for in any migration/sync plan.

- Scheduled tasks: nightly (02:15) and weekly (Sun 03:00) Artifactory backup, staging cleanup (04:00), all under /app/artifactorybackup/bin/. Daily Secrets Manager backup job present but currently disabled (commented out).

- Recurring non-fatal DNS resolution errors observed in dockerd logs for hostname "artifactory-node1" — worth a quick look but not currently service-impacting.

3. Requirements for the CI Test Environment (from CXN-362)

CXN-362 ("Create CI testing environment," parent: CXN-86 Deployment Pipelines) already captures planning notes from the team. Summarized below by category:

## 3.1 Infrastructure

- Stand up a new instance of Bamboo, Bitbucket, and Artifactory in the management VPC — new hostnames/domains (e.g., bamboo-test).

- Deploy 3 new EC2 hosts (one Atlassian, one Artifactory, one Bamboo Agent)

- Create Route53 domains: bamboo-test.mgmt.cnxs.vpcaas.fcs.gsa.gov, bitbucket-test.mgmt.cnxs.vpcaas.fcs.gsa.gov, artifactory-test.mgmt.cnxs.vpcaas.fcs.gsa.gov (plus any additional domain TBD).

## 3.2 Migration

- Migrate all Docker images, volumes, and data.

- Bamboo should auto-generate its own keystore rather than reusing production's.

- New TLS certificates required (Let's Encrypt planned).

- Rename/reuse Docker config files (/usr/local/bin) where possible rather than rebuilding from scratch.

- Search spec and script files for hardcoded production URLs and replace with test URLs.

## 3.3 Access, SSO & Networking

- Confirm git access to Bitbucket repos from the test environment.

- Confirm app links between Bitbucket and Bamboo function correctly.

- Confirm Bamboo can deploy artifacts to the test Artifactory instance.

- Single sign-on: Gavin believes SSO will be needed for the test environment; a separate ticket needs to be entered to track SSO setup, coordinate with Gavin.

- Confirm connectivity from Bamboo server to build agents, and that builds actually execute (not simply queue).

- Confirm service account access to Artifactory from build agents across multiple repos.

## 3.4 Data Sync / Repo Mirroring

- Need one-way mirroring from the Production Conexus repo to the Test Conexus repo (scope: confirm whether other repos also need this).

- The DISC-GSA mirroring script may be reusable rather than writing new tooling.

- Per Bob's input: syncing historical/prior-release repo state is not required  reconciliation is domain-based and the snapshot version is determined by the latest version in the repo at time of run.

## 3.5 Licensing & Risk Acceptance

- Atlassian/JFrog licensing for a second (test) environment needs investigation, action assigned to Gavin.

- The team has accepted, as a known limitation, that true cache-behavior parity would require a full 1:1 clone of production  not planned for this environment, treated as an accepted risk similar to the existing DISC environment.

## 3.6 Validation / Sign-off Checklist

## CXN-362 defines a two-tier review before the environment is considered ready:

- DevOps Check (reviewer other than the implementer) — verify plans, artifacts, and repos; confirm git access, app links, artifact deploys, SSO, and that production instances show no impact from test-environment activity.

- Developer Check — same verification set, plus confirming build logs are complete (nothing built that isn't reflected in logs, consistent with production behavior).

- Update architecture diagrams (Jen/Peter to be informed once the environment is live).

- First live change to validate the process: update scripts to run with anonymous access removed, reviewed via pull request (Das).

- Longer-term open question: once the test process is solid, how is a change promoted from test to production? Team is considering whether Bamboo Specs importer should be used to guarantee code consistency/quality between environments.

## 3.7 Future Improvements (flagged, not required for initial stand-up)

- Review build plan interdependencies across repos to optimize ordering/dependencies.

- Convert inline invocation/commands in build plans into a shared, parameterized common script.

4. Proposed Level of Effort / Work Breakdown

Grouped into sequential phases. Effort is a rough planning estimate pending team review actual sizing should be revisited once licensing and SSO answers come back.

| Phase | Work Items | Owner(s) | Rough Effort |
| --- | --- | --- | --- |
| 1. Provisioning | Stand up 2 new EC2 hosts (Atlassian, Artifactory); decide on/provision agent capacity; create EFS filesystem(s); size storage volumes to mirror prod ratios | DevOps/Titans | 3 days |
| 2. Networking & DNS | Create 3 Route53 records; confirm traffic; validate connectivity from agents to new Bamboo server | DevOps/Titans | 1 day |
| 3. Certs & Identity | Issue Let's Encrypt certs for new domains; open SSO ticket with Gavin and implement once scoped | DevOps + Gavin + OKTA | 2–4 days (SSO timeline TBD) |
| 4. Migration | Migrate Docker images/volumes/data; migrate broker keystore and validate; rename/reuse config files; scrub prod URLs from specs/scripts | DevOps/Titans | 4 day |
| 5. Repo Mirroring | Stand up one-way mirror from prod Conexus repo to test repo, reusing DISC-GSA script where possible | DevOps/Titans | 1–2 days |
| 6. Functional Validation | Confirm git/app-link/artifact-deploy/SSO/agent connectivity/build-execution items per CXN-362 checklist; confirm zero impact to prod | DevOps + Dev reviewer | 2 days |
| 7. Sign-off & Rollout | DevOps Check (peer) + Developer Check; run first live validation change (script update, anonymous access removed) via PR; update architecture diagrams | Das (review), Jeff (implement), Jen/Peter (diagrams) | 2–3 days |

Total rough estimate: ~15–18 working days of effort, excluding any wait time on licensing decisions or SSO configuration, which may run in parallel but could gate final sign-off.

5. Cost & Licensing Considerations

- Compute: 3 new EC2 instances (Atlassian-class + Artifactory-class + Bamboo-Agent-class). Right-sizing candidates based on current prod usage: the Atlassian host runs comfortably on t3.2xlarge (37% root, 87% /app), and Artifactory on m6i.xlarge (52% /app/jfrog) — test environment could reasonably start smaller if load is expected to be lighter than prod, pending team input.

- Storage: EFS for the test environment (cost scales with usage — Artifactory's filestore alone is 400G+ in prod, though a full clone is not planned).

- Licensing: Atlassian (Bamboo, Bitbucket) and JFrog (Artifactory) license terms for a second, non-production instance need confirmation, assigned to Gavin. This could mean an additional paid license tier, a dev/test license exception, or reuse of an existing license depending on vendor terms.

- Certificates: Let's Encrypt is free, avoiding incremental cert cost.

- SSO: cost/effort depends on which identity provider integration is required — TBD pending the ticket Gavin will coordinate.

- Data transfer: one-way repo mirroring and Docker image/volume migration will incur some intra-VPC data transfer cost, expected to be minor relative to compute/storage.

6. Open Questions

- Scope of one-way repo mirroring — is it limited to the Conexus repo, or do other repos need it too?

- What licensing model will Atlassian/JFrog offer for a test instance, and what is the cost/lead time?

- Is SSO a hard requirement for launch, or can the environment go live first with local auth and add SSO after?

- What is the process/tooling for promoting a validated change from test to production once the process is proven? (Bamboo Specs importer under consideration.)